## prioriy List
Priority | User Story Number | Description | Assigned to | Status
1 | 1 | As the System Administrator I want to be able to receive and import Datasets | Carl | Researching
2 | 3 | As the System Administrator I want to have incoming records checked for consistency (i.e. valid date / time values, valid MNC / MCC combinations, valid Event IDs, Cause Codes etc.) and have erroneous records highlighted and excluded | Carl | Researching
3 | 2 | As the System Administrator I want to be able to assign an Id and password to each User type (i.e. Customer Service Rep., Support Engineer, Network Management Engineer) | Dimitar & Ciaran | Researching
4 | 4 | As Customer Service Rep. I want to display, for a given affected IMSI, the Event ID and Cause Code for any / all failures affecting that IMSI | Sahar | Researching
5 | 7 | As a Support Engineer I want to see a list of all IMSIs with call failures during a given time period
6 | 8 | As a Support Engineer I want to count, for a given model of phone, the number of call failures it has had during a given time period.
7 | 9 | As a Network Management Engineer I want to count, for each IMSI, the number of call failures and their total duration during a given time period
8 | 10 | As a Network Management Engineer I want to see, for a given model of phone, all the unique failure Event Id and Cause Code combinations they have exhibited and the number of occurrences.
9 | 19 | As a System Administrator I want to be able to execute data import and update to the Call Failures database automatically as datasets become available
10 | 20 | As any type of User I want to have a response time of < 2s for any query I initiate
11 | 21 | As the System Administrator I want data import and update to the Call Failures database to be executed in < 2 minutes for a dataset of 30,000 records
12 | 5 | As a Customer Service Rep, I want to count, for a given IMSI, the number of failures they have had during a given time period.
13 | 15 | As a Support Engineer I want to be able to access any Customer Service Rep. enquiry, count or report function
14 | 16 | As a Network Management Engineer I want to be able to access any Customer Service Rep. or Support Engineer enquiry, count or report function
15 | 11 | As a Network Management Engineer I want to see the Top 10 Market/Operator/Cell ID combinations that had call failures during a time period
16 | 13 | As a Network Management Engineer I want to see a Graphical Representation of the Top 10 Market/Operator/Cell ID combinations with call failures showing Node, Number of failures & % of all failures
17 | 6 | As a Customer Service Rep. I want to see, for a given IMSI, all the unique Cause Codes associated with its call failures
18 | 12 | As a Network Management Engineer I want to see the Top 10 IMSIs that had call failures during a time period
19 | 14 | As a Support Engineer I want to display, for a given failure Cause Class, the IMSIs that were affected.
20 | 17 | As a Network Management Engineer I want all my queries to have a relevant Graphical representation to augment the numerical data being returned by the query
21 | 18 | As a Network Management Engineer I want to have a range of "drill down" capabilities on my Graphical Representations (e.g. Click on a Cell ID, see the associated failures, click on a failure, see the details etc.) OR (click on a Cause Class, drill down to the Cells affected, show the total duration of failures etc. etc.)

## Sprint 0
Tasks | Assigned to | Status
Review the brief and the initial dataset | All | Done
Review the initial Query List | Sahar | Done
Provide the user stories to the product owner to poulate the Product Backlog | All
Basic Dataset import and Database setup | All | Done
Simple Query
The prototype should also contain the basic scalable architecture for the application

## Queries
Input | Output | By Who | Notes
Dataset | Dataset | System Administrator | Should be able to receive and import
Dataset | Incorrect records highlighted and excluded | System Administrator
ID & Password | Changes to user accounts | System Administrator | Assigned to each time of user
IMSI | Event ID, Cause Code for all affecting failures | Customer Services Rep
Time period | List of all IMSIs with call failures in the given time period | Support Engineer
Model of phone and time period | Number of call failures it has in the given time period | customer Services Rep
IMSI and time period | Number of call failures and their total duration | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Model of phone | All unique failure Event ID and cause code combinations and number of occorunces | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Dataset | Updated Call Failures | System Administrator | As data becomes available
- | - | Support Engineer | Access to all Customer Services rep queries
- | - | Network Management Engineer | Access to any Customer Services rep or Support Engineer enquiry
IMSI and time period | Number of call failures it has in the given time period | Customer Services Rep
Time period | Top 10 Market/Operator/Cell ID combinations that had call failures during a time period | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
IMSI | Number of call failures and their total duration | Support Engineer
Time period | Top 10 IMSIs that had call failures | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Failure Cause Class | IMSIs affected | Support Engineer
2 second query
2 minute import and update data
"First line" queries
Investigating Problems
Evaluation

## Sheet4
|  | Assignee | Status | estimation | actual
DB -> Persistence Layer -> Service Layer -> Presentation Layer -> user response/request
DB
createTables.sql | understand data | Ciaran | Done | 8 | 16
decide data types for cols
give sizes(work with loadTables to perfect this)
implement relationships
implement pks and composite keys
loadTables.sql | parse csv | Carl | Done | 8 | 16
store
Persistence Layer
Generic DAO | Set up interface to detail the methods to be implemented
getAllInfo()
add()
getById()
update()
remove()
Generic Implementation | Create Simple queries, in overwritten methods
execute them with an entity manager
Specific | BaseDataDao | David | Done | 1 | 1
| BaseDataDaoImpl | David | Done | 8 | 8
| EventCauseDao | Carl | Done | 1 | 1
| EventCauseDaoImpl | Carl | Done | 8 | 6
| FailureClassDao | David | Done | 1 | 1
| FailureClassDaoImpl | David | Done | 8 | 4
| MccMncDao | Dimitar | Done | 1 | 1
| MccMncDaoImpl | Dimitar | Done | 8 | 8
| UeDao | Sahar | Done | 1 | 1
| UeDaoImpl | Sahar | Done | 8 | 8
| UserDao | Ciaran | Done | 1 | 1
| UserDaoImpl | Ciaran | Done | 8 | 8
persistence.xml | add data source | Carl | Done | 1 | 1
| add entity classes | Various | Done | 1 | 1
| add db connection settings | Carl | Done | 1 | 1
Service Layer
Generic Entity | map db table cols to variables and
setup empty public constructor
setup full constructor
getters and setters
annotate everything
Specific Entities | BaseDataEntity | David | Done | 4 | 8
| EventCauseEntity | Carl | Done | 8 | 10
| FailureClassEntity | David | Done | 4 | 4
| MccMncEntity | Dimitar | Done | 6 | 6
| UeEntity | Sahar | Done | 4 | 4
| UserEntity | Ciaran | Done | 2 | 2
Other | Named Query in EventCauseEntity for composite keys | Carl | Done | 1 | 1
| Named Query in MccMncEntity for composite keys | Dimitar | Done | 1 | 1
Generic Service | Set up interface to detail the methods to be implemented
getAllInfo()
add()
getById()
update()
remove()
Generic EJB | Create a DAO
implement methods from generic service with DAOs methods
Specific | BaseDataService | David | Done | 1 | 1
| BaseDataServiceEjb | David | Done | 1 | 1
| EventCauseService | Carl | Done | 1 | 1
| EventCauseServiceEjb | Carl | Done | 1 | 1
| FailureClassService | David | Done | 1 | 1
| FailureClassServiceEjb | David | Done | 1 | 1
| MccMncService | Dimitar | Done | 1 | 1
| MccMncServiceEjb | Dimitar | Done | 1 | 1
| UeService | Sahar | Done | 1 | 1
| UeServiceEjb | Sahar | Done | 1 | 1
| UserService | Ciaran | Done | 1 | 1
| UserServiceEjb | Ciaran | Done | 1 | 1
REST
Generic Rest | create an EJB
create() using the ejb
read() using the ejb
readAll() using the ejb
update() using the ejb
delete() using the ejb
Annotations
Specific
| BaseDataRest | David | Done | 4 | 4
| EventDataRest | Carl | Done | 4 | 6
| FailureClassRest | David | Done | 4 | 4
| MccMncRest | Dimitar | Done | 4 | 6
| RagnarRest | Carl | Done | 4 | 6
| UeRest | Sahar | Done | 4 | 6
| UserRest | Ciaran | read() done only for login purposes | 2 | 4
BaseData.upload() |  | Carl | Ongoing | 8
Presentation Layer
DataWatcher | write WatchService | Carl | Ongoing | 4
DataCleaner | open csv | Carl | Done | 2 | 2
open temp file
parse csv
explicitly replace nulls
reformat dates
write to temp
replace original file
DataChanger |  | Sahar | Done | 3 | 6
index.html | display db info | David | Done | 1 | 1
login.html | simple login form | Ciaran | Done | 1 | 1
Generic Crud JS | Create an object based on entity
create()
read()
update()
delete()
readAll()
Specific | base_data_crud.js | David | Done | 3 | 6
| event_cause_crud.js | Carl | Done | 6 | 6
| failure_class_crud.js | David | Done | 3 | 2
| file_upload.js | Carl | Done | 8 | 4
| mcc_mnc_crud.js | Dimitar | Done | 4 | 6
| ue_crud.js | Sahar | Done | 4 | 6
| user_crud.js | Ciaran | read() and matches user data | 8 | 16
basic.css | some styling | Ciaran | Done | 1 | 1
Other
Testing | Simple Arquillian Test on simple data | David | Done | 4 | 16
Testing Enterprise classes
|  |  |  | 205 | 256 | Totals