## prioriy List
Priority | User Story Number | Description | Assigned to | Status
1 | 1 | As the System Administrator I want to be able to receive and import Datasets | Carl | Researching
2 | 3 | As the System Administrator I want to have incoming records checked for consistency (i.e. valid date / time values, valid MNC / MCC combinations, valid Event IDs, Cause Codes etc.) and have erroneous records highlighted and excluded | Carl | Researching
3 | 2 | As the System Administrator I want to be able to assign an Id and password to each User type (i.e. Customer Service Rep., Support Engineer, Network Management Engineer) | Dimitar & Ciaran | Researching
4 | 4 | As Customer Service Rep. I want to display, for a given affected IMSI, the Event ID and Cause Code for any / all failures affecting that IMSI | Sahar | Researching
5 | 7 | As a Support Engineer I want to see a list of all IMSIs with call failures during a given time period
6 | 8 | As a Support Engineer I want to count, for a given model of phone, the number of call failures it has had during a given time period.
7 | 9 | As a Network Management Engineer I want to count, for each IMSI, the number of call failures and their total duration during a given time period
8 | 10 | As a Network Management Engineer I want to see, for a given model of phone, all the unique failure Event Id and Cause Code combinations they have exhibited and the number of occurrences.
9 | 19 | As a System Administrator I want to be able to execute data import and update to the Call Failures database automatically as datasets become available
10 | 20 | As any type of User I want to have a response time of < 2s for any query I initiate
11 | 21 | As the System Administrator I want data import and update to the Call Failures database to be executed in < 2 minutes for a dataset of 30,000 records
12 | 5 | As a Customer Service Rep, I want to count, for a given IMSI, the number of failures they have had during a given time period.
13 | 15 | As a Support Engineer I want to be able to access any Customer Service Rep. enquiry, count or report function
14 | 16 | As a Network Management Engineer I want to be able to access any Customer Service Rep. or Support Engineer enquiry, count or report function
15 | 11 | As a Network Management Engineer I want to see the Top 10 Market/Operator/Cell ID combinations that had call failures during a time period
16 | 13 | As a Network Management Engineer I want to see a Graphical Representation of the Top 10 Market/Operator/Cell ID combinations with call failures showing Node, Number of failures & % of all failures
17 | 6 | As a Customer Service Rep. I want to see, for a given IMSI, all the unique Cause Codes associated with its call failures
18 | 12 | As a Network Management Engineer I want to see the Top 10 IMSIs that had call failures during a time period
19 | 14 | As a Support Engineer I want to display, for a given failure Cause Class, the IMSIs that were affected.
20 | 17 | As a Network Management Engineer I want all my queries to have a relevant Graphical representation to augment the numerical data being returned by the query
21 | 18 | As a Network Management Engineer I want to have a range of "drill down" capabilities on my Graphical Representations (e.g. Click on a Cell ID, see the associated failures, click on a failure, see the details etc.) OR (click on a Cause Class, drill down to the Cells affected, show the total duration of failures etc. etc.)

## Sprint 0
Tasks | Assigned to | Status
Review the brief and the initial dataset | All | Done
Review the initial Query List | Sahar | Done
Provide the user stories to the product owner to poulate the Product Backlog | All
Basic Dataset import and Database setup | All | Done
Simple Query
The prototype should also contain the basic scalable architecture for the application

## Queries
Input | Output | By Who | Notes
Dataset | Dataset | System Administrator | Should be able to receive and import
Dataset | Incorrect records highlighted and excluded | System Administrator
ID & Password | Changes to user accounts | System Administrator | Assigned to each time of user
IMSI | Event ID, Cause Code for all affecting failures | Customer Services Rep
Time period | List of all IMSIs with call failures in the given time period | Support Engineer
Model of phone and time period | Number of call failures it has in the given time period | customer Services Rep
IMSI and time period | Number of call failures and their total duration | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Model of phone | All unique failure Event ID and cause code combinations and number of occorunces | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Dataset | Updated Call Failures | System Administrator | As data becomes available
- | - | Support Engineer | Access to all Customer Services rep queries
- | - | Network Management Engineer | Access to any Customer Services rep or Support Engineer enquiry
IMSI and time period | Number of call failures it has in the given time period | Customer Services Rep
Time period | Top 10 Market/Operator/Cell ID combinations that had call failures during a time period | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
IMSI | Number of call failures and their total duration | Support Engineer
Time period | Top 10 IMSIs that had call failures | Network Management Engineer | Includes Graphical representation w/ drill down capabilities
Failure Cause Class | IMSIs affected | Support Engineer
2 second query
2 minute import and update data
"First line" queries
Investigating Problems
Evaluation

## Sheet4
|  | Assignee | Status | estimation | actual
DB -> Persistence Layer -> Service Layer -> Presentation Layer -> user response/request
DB
createTables.sql | understand data | Ciaran | Done | 8 | 16
decide data types for cols
give sizes(work with loadTables to perfect this)
implement relationships
implement pks and composite keys
loadTables.sql | parse csv | Carl | Done | 8 | 16
store
Persistence Layer
Generic DAO | Set up interface to detail the methods to be implemented
getAllInfo()
add()
getById()
update()
remove()
Generic Implementation | Create Simple queries, in overwritten methods
execute them with an entity manager
Specific | BaseDataDao | David | Done | 1 | 1
| BaseDataDaoImpl | David | Done | 8 | 8
| EventCauseDao | Carl | Done | 1 | 1
| EventCauseDaoImpl | Carl | Done | 8 | 6
| FailureClassDao | David | Done | 1 | 1
| FailureClassDaoImpl | David | Done | 8 | 4
| MccMncDao | Dimitar | Done | 1 | 1
| MccMncDaoImpl | Dimitar | Done | 8 | 8
| UeDao | Sahar | Done | 1 | 1
| UeDaoImpl | Sahar | Done | 8 | 8
| UserDao | Ciaran | Done | 1 | 1
| UserDaoImpl | Ciaran | Done | 8 | 8
persistence.xml | add data source | Carl | Done | 1 | 1
| add entity classes | Various | Done | 1 | 1
| add db connection settings | Carl | Done | 1 | 1
Service Layer
Generic Entity | map db table cols to variables and
setup empty public constructor
setup full constructor
getters and setters
annotate everything
Specific Entities | BaseDataEntity | David | Done | 4 | 8
| EventCauseEntity | Carl | Done | 8 | 10
| FailureClassEntity | David | Done | 4 | 4
| MccMncEntity | Dimitar | Done | 6 | 6
| UeEntity | Sahar | Done | 4 | 4
| UserEntity | Ciaran | Done | 2 | 2
Other | Named Query in EventCauseEntity for composite keys | Carl | Done | 1 | 1
| Named Query in MccMncEntity for composite keys | Dimitar | Done | 1 | 1
Generic Service | Set up interface to detail the methods to be implemented
getAllInfo()
add()
getById()
update()
remove()
Generic EJB | Create a DAO
implement methods from generic service with DAOs methods
Specific | BaseDataService | David | Done | 1 | 1
| BaseDataServiceEjb | David | Done | 1 | 1
| EventCauseService | Carl | Done | 1 | 1
| EventCauseServiceEjb | Carl | Done | 1 | 1
| FailureClassService | David | Done | 1 | 1
| FailureClassServiceEjb | David | Done | 1 | 1
| MccMncService | Dimitar | Done | 1 | 1
| MccMncServiceEjb | Dimitar | Done | 1 | 1
| UeService | Sahar | Done | 1 | 1
| UeServiceEjb | Sahar | Done | 1 | 1
| UserService | Ciaran | Done | 1 | 1
| UserServiceEjb | Ciaran | Done | 1 | 1
REST
Generic Rest | create an EJB
create() using the ejb
read() using the ejb
readAll() using the ejb
update() using the ejb
delete() using the ejb
Annotations
Specific
| BaseDataRest | David | Done | 4 | 4
| EventDataRest | Carl | Done | 4 | 6
| FailureClassRest | David | Done | 4 | 4
| MccMncRest | Dimitar | Done | 4 | 6
| RagnarRest | Carl | Done | 4 | 6
| UeRest | Sahar | Done | 4 | 6
| UserRest | Ciaran | read() done only for login purposes | 2 | 4
BaseData.upload() |  | Carl | Ongoing | 8
Presentation Layer
DataWatcher | write WatchService | Carl | Ongoing | 4
DataCleaner | open csv | Carl | Done | 2 | 2
open temp file
parse csv
explicitly replace nulls
reformat dates
write to temp
replace original file
DataChanger |  | Sahar | Done | 3 | 6
index.html | display db info | David | Done | 1 | 1
login.html | simple login form | Ciaran | Done | 1 | 1
Generic Crud JS | Create an object based on entity
create()
read()
update()
delete()
readAll()
Specific | base_data_crud.js | David | Done | 3 | 6
| event_cause_crud.js | Carl | Done | 6 | 6
| failure_class_crud.js | David | Done | 3 | 2
| file_upload.js | Carl | Done | 8 | 4
| mcc_mnc_crud.js | Dimitar | Done | 4 | 6
| ue_crud.js | Sahar | Done | 4 | 6
| user_crud.js | Ciaran | read() and matches user data | 8 | 16
basic.css | some styling | Ciaran | Done | 1 | 1
Other
Testing | Simple Arquillian Test on simple data | David | Done | 4 | 16
Testing Enterprise classes
|  |  |  | 205 | 256 | Totals

## Sheet4 (2)
|  | Assignee | Status | estimation | actual
DB -> Persistence Layer -> Service Layer -> Presentation Layer -> user response/request
DB | [6 empty] | Total Estimated Time Remaining | Total Actual Time Remaining | Weeks
createTables.sql | understand data | Ciaran | Done | 8 | 16 |  | 193 | 224 | 0.083333
loadTables.sql | parse csv | Carl | Done | 8 | 16 |  | 185 | 208 | 0.16667
Specific | BaseDataDao | David | Done | 1 | 1 |  | 184 | 207 | 0.25
| BaseDataDaoImpl | David | Done | 8 | 8 |  | 176 | 199 | 0.33333
| EventCauseDao | Carl | Done | 1 | 1 |  | 175 | 198 | 0.41667
| EventCauseDaoImpl | Carl | Done | 8 | 6 |  | 167 | 192 | 0.5
| FailureClassDao | David | Done | 1 | 1 |  | 166 | 191 | 0.58333
| FailureClassDaoImpl | David | Done | 8 | 4 |  | 158 | 187 | 0.66667
| MccMncDao | Dimitar | Done | 1 | 1 |  | 157 | 186 | 0.75
| MccMncDaoImpl | Dimitar | Done | 8 | 8 |  | 149 | 178 | 0.83333
| UeDao | Sahar | Done | 1 | 1 |  | 148 | 177 | 0.91667
| UeDaoImpl | Sahar | Done | 8 | 8 |  | 140 | 169 | 1
| UserDao | Ciaran | Done | 1 | 1 |  | 139 | 168 | 1.0833
| UserDaoImpl | Ciaran | Done | 8 | 8 |  | 131 | 160 | 1.1667
persistence.xml | add data source | Carl | Done | 1 | 1 |  | 130 | 159 | 1.25
| add entity classes | Various | Done | 1 | 1 |  | 129 | 158 | 1.3333
| add db connection settings | Carl | Done | 1 | 1 |  | 128 | 157 | 1.4167
Specific Entities | EventCauseEntity | David | Done | 4 | 8 |  | 124 | 149 | 1.5
| FailureClassEntity | Carl | Done | 8 | 10 |  | 116 | 139 | 1.5833
| MccMncEntity | David | Done | 4 | 4 |  | 112 | 135 | 1.6667
| UeEntity | Dimitar | Done | 6 | 6 |  | 106 | 129 | 1.75
| UserEntity | Sahar | Done | 4 | 4 |  | 102 | 125 | 1.8333
| Named Query in EventCauseEntity for composite keys | Ciaran | Done | 2 | 2 |  | 100 | 123 | 1.9167
Other | Named Query in MccMncEntity for composite keys | Carl | Done | 1 | 1 |  | 99 | 122 | 2
| BaseDataService | Dimitar | Done | 1 | 1 |  | 98 | 121 | 2.0833
Specific | BaseDataServiceEjb | David | Done | 1 | 1 |  | 97 | 120 | 2.1667
| EventCauseService | David | Done | 1 | 1 |  | 96 | 119 | 2.25
| EventCauseServiceEjb | Carl | Done | 1 | 1 |  | 95 | 118 | 2.3333
| FailureClassService | Carl | Done | 1 | 1 |  | 94 | 117 | 2.4167
| FailureClassServiceEjb | David | Done | 1 | 1 |  | 93 | 116 | 2.5
| MccMncService | David | Done | 1 | 1 |  | 92 | 115 | 2.5833
| MccMncServiceEjb | Dimitar | Done | 1 | 1 |  | 91 | 114 | 2.6667
| UeService | Dimitar | Done | 1 | 1 |  | 90 | 113 | 2.75
| UeServiceEjb | Sahar | Done | 1 | 1 |  | 89 | 112 | 2.8333
| UserService | Sahar | Done | 1 | 1 |  | 88 | 111 | 2.9167
| UserServiceEjb | Ciaran | Done | 1 | 1 |  | 87 | 110 | 3
| BaseDataRest | Ciaran | Done | 1 | 1 |  | 86 | 109 | 3.0833
| EventDataRest | David | Done | 4 | 4 |  | 82 | 105 | 3.1667
| FailureClassRest | Carl | Done | 4 | 6 |  | 78 | 99 | 3.25
| MccMncRest | David | Done | 4 | 4 |  | 74 | 95 | 3.3333
| RagnarRest | Dimitar | Done | 4 | 6 |  | 70 | 89 | 3.4167
| UeRest | Carl | Done | 4 | 6 |  | 66 | 83 | 3.5
| UserRest | Sahar | Done | 4 | 6 |  | 62 | 77 | 3.5833
|  | Ciaran | read() done only for login purposes | 2 | 4 |  | 60 | 73 | 3.6667
BaseData.upload() | write WatchService | Carl | Ongoing | 8 |  |  | 52 | 73 | 3.75
DataWatcher | open csv | Carl | Ongoing | 4 |  |  | 48 | 73 | 3.8333
DataCleaner |  | Carl | Done | 2 | 2 |  | 46 | 71 | 3.9167
DataChanger | display db info | Sahar | Done | 3 | 6 |  | 43 | 65 | 4
index.html | simple login form | David | Done | 1 | 1 |  | 42 | 64 | 4.0833
login.html | base_data_crud.js | Ciaran | Done | 1 | 1 |  | 41 | 63 | 4.1667
Specific | event_cause_crud.js | David | Done | 3 | 6 |  | 38 | 57 | 4.25
| failure_class_crud.js | Carl | Done | 6 | 6 |  | 32 | 51 | 4.3333
| file_upload.js | David | Done | 3 | 2 |  | 29 | 49 | 4.4167
| mcc_mnc_crud.js | Carl | Done | 8 | 4 |  | 21 | 45 | 4.5
| ue_crud.js | Dimitar | Done | 4 | 6 |  | 17 | 39 | 4.5833
| user_crud.js | Sahar | Done | 4 | 6 |  | 13 | 33 | 4.6667
| some styling | Ciaran | read() and matches user data | 8 | 16 |  | 5 | 17 | 4.75
basic.css | Simple Arquillian Test on simple data | Ciaran | Done | 1 | 1 |  | 4 | 16 | 4.8333
Testing |  | David | Done | 4 | 16 |  | 0 | 0 | 4.9167
|  |  |  | 201 | 256
Totals