## Sprint 1
| Start Hours | Hours Spent - Week One | Hours Spent - Week Two | Hours Spent - Week Three | Total Hours
US1 | 16 | 4 | 8 | 3 | 15
US2 | 12 | 9 | 0 | 15 | 24
US3 | 8 | 2 | 0 | 6 | 8
US4 | 8 | 1 | 0 | 7 | 8
US7 | 6 | 2 | 0 | 6 | 8
US9 | 2 | 3 | 0 | 15 | 18
US21 | 4 | 1 | 0 | 7 | 8
US5 | 2 | 0 | 0 | 10 | 10
US11 | 6 | 0 | 0 | 4 | 4
US6 | 4 | 2 | 0 | 6 | 8
US12 | 2 | 0 | 0 | 8 | 8
US14 | 2 | 0 | 0 | 1 | 1
Actual Remaining Hours | 72 | 48 | 40 | -48
Estimated Remaining Hours | 72 | 48 | 24 | 0

## Sprint 2
|  |  |  | 2017-04-12 | 2017-04-19 | 2017-04-24 | 2017-04-25 | 2017-04-26
Task | Assigned To | Estimated Hours | Actual Hours | 1 | 2 | 3 | 4 | 5
Connected all tables in db and java | Ciaran | 8 | 8 | 8 | 0 | 0 | 0 | 0
Implement bootstrap and link what we already have | David | 8 | 12 | 6 | 0 | 0 | 4 | 2
Planned Bootstrap layout | Ciaran | 2 | 2 | 0 | 0 | 2 | 0 | 0
Bootstrap Log in | Dimitar | 4 | 6 | 4 | 0 | 2 | 0 | 0
Bootsrap | David | 6 | 6 | 2 | 4 | 0 | 0 | 0
Bootstrap - Navigation | Ciaran | 8 | 12 | 0 | 6 | 0 | 6 | 0
Bootstrap - User Restrictions | Ciaran | 6 | 16 | 0 | 8 | 8 | 0 | 0
Bootstrap - All Queries | David | 24 | 20 | 0 | 8 | 6 | 4 | 2
Arquillian Testing - Create Container | David | 4 | 16 | 8 | 0 | 0 | 0 | 8
Arquillian Testing - Research & attempt | Dimitar | 16 | 24 | 1 | 7 | 0 | 8 | 8
Arquillian Testing - Research & attempt | Sahar | 4 | 8 | 0 | 0 | 0 | 0 | 8
Implement Final User Stories | Carl | 2 | 5 | 0 | 5 | 0 | 0 | 0
Written test for user entities | Dimitar | 4 | 16 | 0 | 8 | 0 | 8 | 0
User Story 8 | Carl | 2 | 4 | 0 | 4 | 0 | 0 | 0
User Story 10 | Carl | 2 | 1 | 0 | 1 | 0 | 0 | 0
Restrictions on Queries and Bootstrap merge | Ciaran | 4 | 8 | 0 | 8 | 0 | 0 | 0
User Story 15 | Carl | 3 | 2 | 0 | 2 | 0 | 0 | 0
User Story 16 | David | 3 | 3 | 0 | 3 | 0 | 0 | 0
User Story 13 | Ciaran | 3 | 2 | 0 | 0 | 2 | 0 | 0
User Story 17 | Dimitar | 3 | 3 | 0 | 3 | 0 | 0 | 0
User Story 18 | David | 3 | 1 | 0 | 0 | 1 | 0 | 0
Implement User Sessions in EJB to keep track of Login info | Carl | 6 | 8 | 0 | 0 | 6 | 2 | 0
Graphs - Research Graphs | Sahar | 2 | 3 | 3 | 0 | 0 | 0 | 0
Graphs - Written HTML for Us12 | Sahar | 2 | 4 | 0 | 4 | 0 | 0 | 0
Graphs - Insert Data into Graph 12 | Sahar | 1 | 8 | 0 | 4 | 4 | 0 | 0
Graphs - Written HTML for Us11 | Sahar | 2 | 1 | 0 | 0 | 1 | 0 | 0
Graphs - Insert Data into Graph US11 | Sahar | 1 | 8 | 0 | 0 | 4 | 4 | 0
Graphs - Written HTML for Us9 | Sahar | 1 | 4 | 0 | 0 | 0 | 4 | 0
Graphs - Insert Data into Graph US9 | Sahar | 2 | 2 | 0 | 0 | 0 | 1 | 1
Drilldown on all graphs | Sahar | 4 | 0 | 0 | 0 | 0 | 0 | 0
Refactor to named queries. Try/catch on persist. | Carl | 4 | 4 | 2 | 2 | 0 | 0 | 0
Sessions - Research | Ciaran | 4 | 8 | 3 | 5 | 0 | 0 | 0
User Sessions | Carl | 12 | 16 | 0 | 0 | 8 | 8 | 0
User Logout | Carl | 4 | 3 | 0 | 0 | 0 | 0 | 3
Change US 9 + 11 | David | 1 | 1 | 0 | 0 | 1 | 0 | 0
|  | 165 | 245
Actual Remaining Hours |  | 165 | 165 | 128 | 46 | 1 | -48 | -80
Estimated Remaining Hours |  | 165 | 165 | 132 | 99 | 66 | 33 | 0